## Worksheet
Marketing Planning - Startup Gantt Chart
Task | Start Date | End Date | Status | % Complete
Market Research & Analysis | 2024-01-05 | 2024-01-19 | Pending | 5%
Define Target Audience Persona | 2024-01-16 | 2024-01-30 | Pending | 3%
Create Brand Identity & Messaging | 2024-01-25 | 2024-02-15 | Pending | 8%
Develop Content Strategy | 2024-01-30 | 2024-02-15 | Pending | 6%
Design Marketing Materials (Digital & Print) | 2024-02-10 | 2024-03-15 | Pending | 1%
Launch Website & Landing Pages | 2024-03-01 | 2024-03-31 | Pending | 5%
Initiate Social Media Campaigns | 2024-03-15 | 2024-04-30 | Pending | 7%
Run Paid Advertising (Google & Meta) | 2024-04-01 | 2024-06-30 | Pending | 3%
Host Product Launch Event (Virtual) | 2024-05-15 | 2024-05-16 | Pending | 8%
Measure Results & Optimize Campaigns | 2024-05-17 | 2024-06-30 | Pending | 1%