## Worksheet
Marketing Planning Gantt Chart - Team Use
Task ID | Task Name | Description | Start Date | End Date | Duration (Days) | Status | Assigned To
T001 | Market Research & Analysis | Collect data on target audience and competitors. | 2024-06-15 | 2024-06-30 | 16 |  | Jane Smith (Marketing Research)
T002 | Brand Positioning Strategy | Define unique value proposition and brand voice. | 2024-07-01 | 2024-07-15 | 15 |  | Mark Johnson (Strategy)
T003 | Content Creation Phase 1 | Develop blog posts, social media content, and email templates. | 2024-07-16 | 2024-08-15 | 31 |  | Lisa Chen (Content Team)
T004 | Ad Campaign Design | Create visuals and copy for digital advertising. | 2024-07-30 | 2024-08-15 | 17 |  | Alex Rodriguez (Design)
T005 | Website Optimization | Update landing pages and improve UX for campaign. | 2024-08-16 | 2024-08-31 | 16 |  | Daniel Kim (Web Dev)
M001 | Campaign Launch | Official launch of marketing campaign across all channels. | 2024-09-01 | 2024-09-01 | 1 |  | All Teams
T006 | Performance Monitoring & Reporting | Track KPIs and generate weekly reports. | 2024-09-02 | 2024-11-30 | 91 |  | Sarah Wilson (Analytics)
Legend
Progress Completed
Milestone: Key event or deliverable point