## Worksheet
Marketing Planning - Gantt Chart Template (Template Version)
Task ID | Task Name | Start Date | End Date | Status | % Complete
1.01 | Market Research & Analysis | 2024-04-01 | 2024-04-15 | In Progress | 65%
1.02 | Competitor Benchmarking | 2024-04-16 | 2024-05-01 | Not Started | 0%
2.01 | Create Marketing Strategy Document | 2024-05-01 | 2024-05-15 | Not Started | 0%
3.01 | Creative Asset Development (Designs, Videos) | 2024-05-16 | 2024-06-30 | Not Started | 0%
4.01 | Finalize Channel Strategy & Budget Allocation | 2024-06-15 | 2024-06-30 | Not Started | 0%
5.01 | Campaign Launch (All Channels) | 2024-07-01 | 2024-07-31 | Not Started | 0%
6.01 | Daily Performance Monitoring & Reporting | 2024-07-01 | 2024-08-31 | Not Started | 0%
7.01 | Campaign Performance Analysis & ROI Report | 2024-09-01 | 2024-09-15 | Not Started | 0%
Milestone: Campaign Launch Complete - September 15, 2024