## Worksheet
Marketing Planning - Gantt Chart (Tracking View)
Task ID | Task Name | Start Date | End Date | Status | Progress (%) | Responsible Team
MR-001 | Market Research & Analysis | 2024-06-01 | 2024-06-15 | In Progress | 85% | Research Team
CS-002 | Campaign Strategy Development | 2024-06-16 | 2024-07-15 | In Progress | 75% | Strategy Team
CC-003 | Content Creation (Video & Copy) | 2024-07-16 | 2024-08-15 | To Do | 0% | Content Team
CD-004 | Creative Design & Mockups | 2024-07-16 | 2024-08-15 | To Do | 0% | Design Team
MP-005 | Media Planning & Buying | 2024-08-16 | 2024-10-31 | To Do | 0% | Media Team
CL-006 | Campaign Launch (Phase 1) | 2024-11-01 | 2024-11-30 | To Do | 0% | Launch Team
PT-007 | Performance Tracking & Analytics | 2024-11-01 | 2025-03-31 | To Do | 0% | Data Team
FR-008 | Milestone: Final Campaign Review & Report | 2025-04-15 | 2025-04-15 | Milestone (Pending) | 8% | Project Manager
Note:This Gantt chart is a tracking view for marketing planning. Progress percentages are updated dynamically based on real-time status.