## Worksheet
Marketing Planning - Office Use Template
Marketing Campaign Overview
Phase | Objective | Target Audience | Budget (USD) | Timeline (Start - End) | Status
Research & Analysis | Analyze market trends and customer behavior | Millennials (18-35) | 10,000 | Jan 1 - Jan 31 | In Progress
Campaign Design | Create compelling content and visuals | Gen Z (16-24) | 15,000 | Feb 1 - Feb 28 | Not Started
Promotion & Launch | Drive awareness through digital and social channels | General Public (16+) | 30,000 | Mar 1 - Mar 31 | Not Started
Social Media Engagement | Foster community and interaction on platforms | Active Online Users | 8,000 | Apr 1 - Apr 30 | Not Started
Performance Review | Evaluate ROI and campaign effectiveness | All Stakeholders | 5,000 | May 1 - May 15 | Not Started
Total Estimated Budget: |  |  | 68,000
Notes:
This template is designed for internal office use in marketing planning.
All dates are subject to change based on resource availability and feedback cycles.
Status indicators: Not Started, In Progress, Completed.