## Worksheet
Marketing Planning - Team Use Template
Phase | Activity/Task | Owner(s) | Timeline (Start - End) | Status | Budget Allocation ($)
Team Use: Fill in marketing initiatives and tracking details below.
Research & Planning | Market research and competitor analysis | Marketing Team | Jan 01 - Jan 15, 2024 | In Progress | $3,500
Strategy Development | Create marketing objectives and KPIs | Marketing Lead, Strategy Team | Jan 16 - Jan 31, 2024 | To Do | $500
Content Creation | Develop campaign materials (videos, graphics, copy) | Content Team, Designers | Feb 1 - Feb 28, 2024 | To Do | $15,000
Channel Planning | Select and schedule digital marketing channels (social media, email, ads) | Digital Marketing Team | Mar 1 - Mar 10, 2024 | To Do | $8,000
Launch Phase | Execute initial campaign rollout across all channels | All Teams (Collaborative) | Mar 11 - Mar 31, 2024 | To Do | $25,000
Performance Review | Analyze campaign metrics and adjust strategies accordingly | Analytics & Marketing Teams | Apr 1 - Apr 15, 2024 | To Do | $3,000
Total Estimated Budget: |  |  |  |  | $55,000
Note:This template is designed for team collaboration in marketing planning. Update status regularly and share with stakeholders.