## Worksheet
Marketing Planning - Invoice Template (Planning View)
Company Information
Name: | Global Marketing Solutions Inc.
Address: | 123 Innovation Drive, Suite 500, San Francisco, CA 94105
Email: | info@globalmarketing.com
Phone: | +1 (415) 555-0123
Invoice Details
Invoice No: | INV-2024-MKT-001
Date: | April 5, 2024
Due Date: | May 5, 2024
Status: | Pending Approval
Marketing Activity | Objective | Channel | Budget (USD) | Schedule (Start - End) | Responsible Team
Email Campaign - Q2 | Boost lead generation by 25% | Email | $8,000 | Apr 1 - Apr 30 | Marketing Team A
Social Media Ads (LinkedIn & Instagram) | Increase brand awareness among professionals | Social Media | <$12,500 | Apr 15 - May 31 | Digital Marketing Team
Webinar Series: "Future of Digital Marketing" | Drive engagement with target customers | Virtual Event | $6,000 | May 10 - May 24 | Events & Content Team
Influencer Partnerships (Tech Space) | Increase reach in tech community | Social Media | $9,500 | Apr 20 - Jun 15 | Partnerships Team
SEO & Content Optimization (Website) | Raise organic traffic by 30% | Content & SEO | $7,200 | Mar 1 - Jun 30 | Digital Team
Total Planned Budget: |  |  | $43,200