## Worksheet
Marketing Planning - Monthly Manager View
Activity / Initiative | Owner | Start Date | End Date | Target Audience | Budget (USD) | KPI Target | Progress (%) | Status | Notes / Risks
Q2 Campaign Launch - Digital Ads | Marketing Team A | 2024-06-01 | 2024-06-30 | B2B, Age 35–55 | $18,500.00 | 12K Leads | 94% | On Track | Minor CTR variance; adjustments ongoing.
Social Media Content Series | Content Team B | 2024-06-05 | 2024-06-30 | All Gen Z & Millennials | $5,300.00 | 1.8M Impressions | 89% | On Track | Slight delay in video production.
Customer Webinar Series (3 Sessions) | Events Team C | 2024-06-10 | 2024-06-28 | Premium Subscribers & Prospects | $3,750.00 | 95% Attendance Rate | 100% | Complete | All sessions successfully delivered.
Email Marketing Funnel Revamp | Email Team D | 2024-06-15 | 2024-06-30 | All Users (Segmented) | $8,900.00 | 3.5% CTR Increase | 71% | Delayed | Design feedback cycle caused 4-day delay.
Trade Show Participation (New York) | Events Team C | 2024-06-18 | 2024-06-30 | B2B Industry Prospects | $45,000.00 | 15K Leads Generated | 38% | On Track | Exhibition prep in progress.
Influencer Partnership Program | PR Team E | 2024-06-12 | 2024-06-30 | Social Audience (Niche) | $14,500.00 | 85K Reach + 7% Engagement Rate | 91% | On Track | Two influencers confirmed; remaining to onboard.
Total Monthly Budget | [8 empty] | $105,950.00
Overall Status Summary | [8 empty] | 83% Complete
Prepared by:Marketing Director – Jane Doe ¦Date:June 2, 2024
Note: This template is designed for monthly planning and performance tracking. Update status weekly.