## Worksheet
Marketing Planning - Monthly Planner
Month: January ¦ Year: 2024 ¦ Team: Marketing Department
Week | Objective | Action Plan | Responsible Team Member | Status
Week 1 (Jan 1 - Jan 7) | Increase brand awareness through social media campaigns | Launch new Instagram and LinkedIn ad campaigns with influencer partnerships | Alice Johnson | Pending
Week 2 (Jan 8 - Jan 14) | Generate leads via content marketing | Publish 3 blog posts and optimize landing pages for SEO | Robert Chen | In Progress
Week 3 (Jan 15 - Jan 21) | Host a webinar on market trends | Create event promo, invite email list, and coordinate with speaker | Sophia Martinez | Pending
Week 4 (Jan 22 - Jan 31) | Analyze campaign performance and adjust strategy | Compile data from analytics tools, prepare monthly report | David Kim | In Progress
Page 1 of 4 ¦ Prepared by: Marketing Department ¦ Confidential
Marketing Planning - Monthly Planner
Month: January ¦ Year: 2024 ¦ Team: Marketing Department
Channel | KPI Target | Actual Result | Progress (%) | Budget Allocated ($)
Facebook Ads | 2,500 impressions ¦ 120 leads | 2,348 impressions ¦ 115 leads | 94% | $3,500
Google Ads | 5,000 clicks ¦ 2% CTR | 4,876 clicks ¦ 2.1% CTR | 97% | $8,000
Email Marketing | 35% open rate ¦ 5% CTR | 34.6% open rate ¦ 4.8% CTR | 99% | $1,200
Social Media (Instagram + LinkedIn) | 5,000 engagements ¦ 8% reach increase | 4,782 engagements ¦ 7.6% reach increase | 95% | $2,300
Page 2 of 4 ¦ Prepared by: Marketing Department ¦ Confidential
Marketing Planning - Monthly Planner
Month: January ¦ Year: 2024 ¦ Team: Marketing Department
Campaign Name | Start Date | End Date | Budget ($) | Status
New Product Launch Campaign | Jan 5, 2024 | Jan 31, 2024 | $18,500 | In Progress
Holiday Promo Drive (Pre-Christmas) | Dec 1, 2023 | Dec 31, 2023 | $14,750 | Completed
Influencer Collaboration Series | Jan 1, 2024 | Jan 31, 2024 | $9,850 | In Progress
Social Media Challenge: #MyBrandMoment | Jan 10, 2024 | Jan 31, 2024 | $6,500 | In Progress
Page 3 of 4 ¦ Prepared by: Marketing Department ¦ Confidential
Marketing Planning - Monthly Planner
Month: January ¦ Year: 2024 ¦ Team: Marketing Department
Task | Due Date | Priority | Dependencies | Notes/Comments
Create campaign storyboard for social media content | Jan 6, 2024 | High | Brief from product team received | Approved by design lead on Jan 5.
Finalize influencer contracts and agreements | Jan 8, 2024 | High | List of selected influencers approved | Negotiations ongoing with top 3.
Develop webinar presentation materials | Jan 14, 2024 | MediumScheduled for Jan 18, speaker confirmedSlides to be reviewed by marketing director.
Send post-campaign survey to participants | Jan 25, 2024 | Low | All campaigns completed or in final phaseEmail automation set up for delivery.