## Worksheet
Marketing Planning - Monthly Planner
Planning View ¦ Month:April 2025
Task / Activity | Channel | Owner | Schedule (Date) | Status | KPIs / Target | Action Required
Q2 Campaign Strategy Finalization | All Channels | Marketing Manager | 2025-04-05 | Pending | Campaign approval & budget allocation complete | Review Drafts, Share Feedback
Content Calendar Development (April) | Blog, Social Media | Content Team | 2025-04-10 | Pending | 15 posts published across platforms | Finalize themes, assign topics
Email Marketing Series Launch (April) | Email | Marketing Coordinator | 2025-04-15 | Pending | Open rate ≥ 35%, CTR ≥ 8% | Send test emails, verify links
Social Media Ad Campaign (April) | Facebook, Instagram | Media Buyer | 2025-04-18 | Pending | CPC ≤ $1.20, ROAS ≥ 3.5x | Review creatives, set targeting rules
Webinar: Product Launch Preview | Live Streaming, Webinar Platform | Events Manager | 2025-04-23 | Pending | 150+ registrations, 75% attendance rate | Confirm speakers, send invites
Monthly Performance Review Meeting | All Departments | Marketing Director | 2025-04-30 | Pending | Analyze KPIs, adjust Q2 strategy | Compile reports, prepare slides
Competitor Benchmark Analysis Report | Research & Insights | Data Analyst | 2025-04-28 | Pending | Comprehensive competitor activity overview | Gather data, summarize findings
Customer Feedback Survey (April) | Survey Tool, Email | UX Researcher | 2025-04-12 | Pending | Target 300 responses, ≥85% satisfaction rate | Design survey, distribute to customers
LinkedIn Thought Leadership Series | LinkedIn Articles | Content Writer | 2025-04-14 & 04-26 | Pending | 3 articles published, ≥50 engagements each | Draft content, schedule posts
SEO Optimization Audit (Site-Wide) | Website & Blog | SEO Specialist | 2025-04-25 | Pending | Fix 90% of technical SEO issues | Run audit tools, submit fixes list
Partner Co-Marketing Proposal Draft | Strategic Partnerships | Partnership Manager | 2025-04-20 | Pending | 1 proposal submitted for review by 3 partners | Draft, collect partner input, finalize
April Marketing Budget Review & Forecast | Finance & Planning | Finance Analyst | 2025-04-30 | Pending | Budget variance ≤ 5%, forecast accuracy ≥90% | Update spend reports, run forecast model
Customer Retention Campaign (April) | Email, SMS | Retention Specialist | 2025-04-27 | Pending | Re-engagement rate ≥ 15% | Segment audience, create messaging
Content Repurposing Initiative (Q2) | All Content Channels | Content Manager | 2025-04-08 | Pending | Create 6 repurposed assets from top-performing content | Identify high-performing pieces, plan formats
Internal Marketing Training (April) | Team Development | HR & Learning Lead | 2025-04-16 | Pending | 85% team attendance, post-training survey score ≥4.7/5.0 | Schedule session, prepare materials