## Worksheet
Marketing Planning - Business Use Planner
Marketing Strategy Overview
Phase 1: Market Analysis & Research
Objective | Key Metrics | Target Audience | Research Methods | Status (Progress) | Deadline
Analyze customer demographics and behavior trends. | Market share, engagement rate, conversion funnel drop-off. | Age 25-40, urban professionals with mid-to-high income. | Surveys, focus groups, social listening tools. |  | 2024-05-15
Evaluate competitor positioning and campaign strategies. | Share of voice, ad spend, content frequency. | Primary competitors: Brand A, Brand B. | Competitor benchmarking reports, SEMrush analysis. |  | 2024-05-22
Phase 2: Marketing Goals & KPIs
Goal Type | Specific Objective | KPI Target | Budget Allocation ($) | Owner(s) | Due Date
Brand Awareness | Increase brand recall by 30% within Q3. | 30% uplift in unaided awareness | $25,000 | Jane Smith (Marketing Manager) | 2024-11-30
Sales & Conversion | Generate 5,000 qualified leads from digital campaigns. | 5,000 leads with 15% conversion rate | $48,750 | Mike Johnson (Digital Lead) | 2024-12-15
Phase 3: Campaign Execution Plan
Campaign Name | Channels Used | Content Type | Launch Date | Duration (Weeks) | Expected ROI
Social Media Blitz: Summer Campaign | Instagram, LinkedIn, Facebook Ads | Video Reels, Carousel Posts, Stories | 2024-06-15 | 8 weeks | $3.20 per dollar spent
Email Nurture Series: Onboarding Flow | Email Marketing, CRM Automation | Drip campaigns, personalized emails | 2024-07-10 | 6 weeks | $4.50 per dollar spent
Phase 4: Performance Tracking & Review Schedule
Review Period | Metrics Tracked | Data Source | Reporting Frequency | Responsible Team Member | Next Review Date
Monthly (Q3) | CTR, CPM, Cost per Lead, Conversion Rate | Google Analytics, Meta Ads Manager, HubSpot | Every 4 weeks | Sarah Lee (Analytics Team) | 2024-07-31
Note: This marketing plan template is designed for business use. Update status and progress quarterly. All data must be validated before reporting to stakeholders.