## Worksheet
Marketing Planning - Client View
Project Overview & Key Objectives
Phase | Timeline (Start - End) | Key Deliverables | Responsible Team | Status | Milestones & KPIs
Market Research & Analysis | Jan 1, 2024 - Feb 15, 2024 | Competitor analysis report, customer persona document | Research & Insights Team | In Progress | Cover 5 key competitors, define 3 primary personas with ≥80% accuracy rate
Strategy Development | Feb 16, 2024 - Mar 31, 2024 | Full marketing strategy document, channel mix plan | Marketing Strategy Team | Pending Start | Approved by client by Mar 25, 2024; strategy to include digital & traditional mix
Campaign Creation (Phase 1) | Apr 1, 2024 - May 31, 2024 | Content calendar, ad creatives, landing page drafts | Content & Creative Team | Pending Start | 10 high-performing creatives delivered by Apr 20, 2024
Campaign Launch & Execution | Jun 1, 2024 - Aug 31, 2024 | Live campaigns across platforms, performance dashboards | Media & Performance Team | Pending Start | Reach 50K impressions/week by Week 3; CTR ≥2.5%
Performance Review & Optimization | Sep 1, 2024 - Oct 31, 2024 | Monthly reports, A/B test findings, optimization recommendations | Data Analytics & Optimization Team | Pending Start | Report delivered on time each month; ROI improvement ≥15%
Budget Allocation Summary (USD)
Market Research |  |  | $10,000 | Completed | 100% spent; delivered on time
Content Creation & Design |  |  | $35,000 | In Progress (45%) | Delivered 6 of 12 creative assets by mid-April
Digital Advertising (Paid Media) |  |  | $75,000 | Not Started | Monthly allocation: $25K; budget locked for Q2-Q4
Key Performance Indicators (KPIs)
Objective | Target | Current Status | Last Measurement Date | Note: All KPIs tracked monthly via dashboard.
Website Traffic (Monthly) | 50,000 visits | 32,456 visits | Mar 31, 2024 | ↑18% MoM; on track for Q2 goal.
Lead Conversion Rate | 5.0% | 4.3% | Mar 31, 2024 | Needs optimization; A/B testing underway.
Social Media Engagement Rate | 8.5% | 7.6% | Mar 31, 2024 | Slight lag; increased content frequency planned.
Client Feedback & Approval Status
Strategic Plan Review | Mar 25, 2024 | Approved | Mar 18, 2024 | Client feedback incorporated. All changes updated.
Creative Assets (Phase 1) | Apr 25, 2024 | In Review | Apr 5, 2024 | Client requested minor adjustments to tone and visuals.
Digital Campaign Launch (Q2) | Jun 1, 2024 | Pending Approval | N/A | Awaiting client sign-off on campaign brief and budget.