## Worksheet
Marketing Planning - Detailed Planner Template
Phase | Objective / Goal | Target Audience | Channels & Tactics | Budget Allocation ($) | Schedule (Start - End) | KPIs & Metrics
Strategic Planning Phase
Market Research | Analyze market trends, competitors, and customer needs. | Primary: Age 25-45; Secondary: Tech-savvy professionals. | Surveys, focus groups, social listening tools (e.g., Brandwatch). | 10,000 | Jan 1 – Jan 31 | Survey response rate ≥45%, competitor SWOT completed.
Goal Setting | Define SMART marketing objectives for Q1. | All stakeholders involved in planning. | Workshops, OKR alignment sessions, executive review meetings. | 2,500 | Feb 1 – Feb 7 | S.M.A.R.T. goals documented and approved by leadership.
Tactical Execution Phase
Content Creation | Produce high-quality, brand-aligned content for all channels. | Target audience: Digital-first consumers. | Blogs, videos, infographics, email newsletters (Mailchimp). | 15,000 | Feb 8 – Mar 31 | 24 pieces of content published; average engagement rate ≥6%.
Digital Advertising | Drive awareness and lead generation via paid campaigns. | Demographics: Urban professionals aged 28–40. | Google Ads, Meta Ads, LinkedIn Sponsored Content, YouTube Pre-roll. | 50,000 | Feb 15 – Apr 30 | CPC ≤ $1.25; CTR ≥2.8%; Lead conversion rate ≥3.5%.
Email Campaigns | Build customer loyalty and promote product launches. | Subscribers: Active users (opted-in). | Drip campaigns, segmented email series, A/B testing (HubSpot). | 8,000 | Mar 1 – Apr 30 | Email open rate ≥42%; CTR ≥8%.
Performance Monitoring & Optimization
Analytics & Reporting | Track KPIs and report on campaign performance weekly. | Marketing team, executives, and stakeholders. | Google Analytics 4, Tableau dashboards, monthly reports. | 7,500 | Ongoing (Feb 1 – Apr 30) | Daily monitoring logs; weekly performance reports delivered.
A/B Testing & Optimization | Improve campaign effectiveness through iterative testing. | All digital campaign audiences. | Subject lines, CTAs, visuals, landing pages (Optimizely). | 5,000 | Mar 1 – Apr 30 | Minimum of 3 tests per channel; ≥15% improvement in conversion.
Final Review & Planning (Q2)
Post-Mortem Analysis | Review Q1 performance, identify wins and gaps. | Marketing team, department heads. | Retrospective meetings, documented insights report. | 3,000 | May 1 – May 7 | All campaigns reviewed; lessons-learned document created.
Q2 Planning Session | Create detailed plan for Q2 based on Q1 outcomes. | Entire marketing leadership team. | Workshops, strategy alignment, budget forecasting. | 4,000 | May 8 – May 15 | Q2 plan approved and shared with stakeholders.
Total Estimated Budget for Q1 |  |  |  | $105,000
Note: All dates and budgets are estimates. Adjustments may be made based on real-time performance and business priorities.