## Worksheet
Marketing Planning - Extended Planner Template
Week / Month | Strategic Goals |  |  | Tactical Actions |  |  |  | Responsible Team | Status
| Objective | KPIs & Targets | Timeline | Action Item 1 | Action Item 2 | Action Item 3
Q1 - Q2 Planning & Strategy Development | [8 empty] | Not Started
Week 1-2 | Define brand positioning and messaging | Brand awareness increase by 20% by Q3 | Q2 Launch | Conduct market research & competitor analysis | Create brand voice guidelines document | Develop initial campaign concepts | Marketing & Branding Team | In Progress
Week 3-4 | Set quarterly marketing targets | 15% increase in lead generation, 30% engagement rate | Q2 End | Create detailed marketing calendar | Finalize budget allocation per channel | Pilot social media content strategy | Marketing Operations Team | On Hold (Pending Approval)
Q2 - Campaign Execution Phase | [8 empty] | Not Started
Week 5-6 | Launch digital advertising campaign | CPL under $10, CTR > 2.5% | Mid-Q2 | Create ad creatives (banners & videos) | Set up Google Ads & Meta Campaigns | Implement conversion tracking pixel | Digital Marketing Team | In Progress
Week 7-8 | Boost content engagement & SEO performance | Website traffic +25%, blog shares >100/month | Q2 End | Publish 4 new blog posts/week | Optimize on-page SEO for target keywords | Launch email newsletter series (bi-weekly) | Content & SEO Team | Pending Review
Q2 - Performance Monitoring & Adjustments | [8 empty] | Not Started
Week 9-10 | Analyze campaign effectiveness and adjust strategy | Determine top-performing channels & tactics by ROI | End of Q2 | Generate performance reports (weekly) | Reallocate budget to high-ROI channels | Conduct team retrospective meeting | Data Analytics Team | Not Started
Week 11-12 | Prepare for Q3 launch planning | Complete Q2 review with actionable insights | Q3 Kick-off | Capture lessons learned from current campaign | Prioritize new initiatives for Q3 | Begin budget forecasting process | Marketing Leadership Team | Not Started
Total Planned Activities | [7 empty] | 6 | Overall Status:
Summary
Total Goals:6 ¦In Progress:2 ¦On Hold:1 ¦Pending Review:1 ¦Completed:2
This extended marketing planning template supports comprehensive quarterly strategy execution, performance tracking, and continuous optimization across multiple channels.