## Worksheet
Marketing Planning - Freelancer Planner Template
Week | Objective | Key Activities | Status | Budget (USD) | Responsible
Marketing Campaign Planning
Week 1 | Define campaign goals and target audience | Conduct market research, analyze competitors, finalize buyer personas | In Progress | $250 | Freelancer A
Week 2 | Develop campaign messaging and creative assets | Create copy, design visuals, develop content calendar | Completed | $650 | Freelancer B
Week 3 | Launch digital ad campaigns (social media & Google) | Create ad sets, set targeting parameters, launch test campaigns | In Progress | $1,200 | Freelancer C
Week 4 | Analyze campaign performance and optimize ads | Review KPIs, adjust targeting, reallocate budget for better ROI | In Progress | $300 | Freelancer C
Content & Social Media Strategy
Week 5 | Plan and schedule monthly content calendar | Create blog topics, video scripts, social media posts | In Progress | $400 | Freelancer D
Week 6 | Publish first wave of content across platforms | Post on LinkedIn, Instagram, Facebook, and blog platform | Completed | $200 | Freelancer D
Week 7 | Engage with audience and grow community presence | Respond to comments, initiate conversations, collaborate with micro-influencers | In Progress | $350 | Freelancer E
Week 8 | Evaluate content performance and refine strategy | Analyze engagement rates, follower growth, click-throughs | In Progress | $150 | Freelancer E
Total Estimated Budget: |  |  |  | $4,800