## Worksheet
Marketing Planning Team Use Template
Week | Objective | Action Items | Owner(s) | Status | Resources Needed
Week 1 | Define campaign goals and target audience | Conduct market research, analyze customer personas, set KPIs | Jane Doe, Alex Lee | Pending | Survey tools, CRM data access
Week 2 | Develop messaging and creative assets | Create ad copy, design visuals, draft email templates | Maria Chen, Tom Wright | In Progress | Design software, brand guidelines
Week 3 | Plan media channels and budget allocation | Select platforms (social, email, PPC), allocate budget | Sam Rivera, Lisa Park | In Progress | Budget tracker spreadsheet, platform analytics access
Week 4 | Launch first campaign phase and monitor performance | Publish content, track clicks/conversions, adjust in real-time | All Team Members | Not Started | Campaign dashboard, analytics tools
Week 5 | Analyze results and optimize strategy | Review metrics, identify bottlenecks, refine messaging | Jane Doe, Maria Chen | Pending | Data visualization tools, meeting room access
Week 6 | Plan next campaign cycle and report to stakeholders | Summarize learnings, prepare presentation deck, share insights | All Team Members | Pending | Presentation software, stakeholder feedback form
Team Use: Updated weekly. Please ensure all entries are reviewed and approved by team leads before submission.