## Worksheet
Marketing Planning - Advanced Project Plan
Task ID | Task Name | Owner | Start Date | End Date | Status | Progress (%) | Prioritization (P1-P3) | Budget (USD)
Phase 1: Market Research & Analysis
MR-001 | Competitor Benchmarking | Sarah Johnson | 2024-04-01 | 2024-04-15 | In Progress | 68% | P1 | $7,500
MR-002 | Customer Persona Development | Luis Mendez | 2024-04-16 | 2024-05-15 | In Progress | 85% | P1 | $6,000
Phase 2: Campaign Strategy & Development
CS-011 | Content Calendar Planning (Q3) | Maria Chen | 2024-05-16 | 2024-07-31 | Completed | 100% | P1 | $5,200
Phase 3: Campaign Execution & Launch
EX-101 | Social Media Campaign Launch - Phase 1 | James Walker | 2024-06-05 | 2024-07-31 | In Progress | 73% | P1 | $18,900
Phase 4: Monitoring & Optimization (Ongoing)
MO-201 | Daily Performance Tracking - KPIs | Aisha Patel | 2024-06-05 | Ongoing | In Progress | 100% | P2 | $3,500/month
Phase 5: Final Reporting & Review (Q3)
RR-301 | Marketing ROI Analysis Report | Ryan Thompson | 2024-10-01 | 2024-10-31 | Delayed | 5% | P2 | $9,800
Total Project Budget: | [6 empty] | $68,900
Notes:
Status values updated on May 3, 2024.
Prioritization levels (P1 = High, P2 = Medium, P3 = Low).
Budgets include personnel, tools, and external vendor costs.