## Worksheet
Marketing Planning - Project Plan - Analysis View
Phase | Activity | Owner | Start Date | End Date | Status | Budget (USD) | Metric Target | Actual Result | KPI Achievement (%)
Market Research & Analysis Phase
1.1 | Competitor Benchmarking | Marketing Analyst | 2024-03-01 | 2024-03-15 | In Progress | $8,500 | Identify 8 competitors with market share > 5% | 6 Competitors Identified | 75%
1.2 | Customer Persona Development | User Researcher | 2024-03-10 | 2024-03-25 | Pending | $12,000 | Create 5 detailed personas with behavioral insights | Not Started | 0%
Campaign Strategy Development Phase
2.1 | Channel Mix Planning | Marketing Strategist | 2024-03-26 | 2024-04-15 | Pending | $15,000 | Determine optimal mix across digital, print, events (70/20/10) | Not Started | 0%
Execution & Measurement Phase
3.1 | Campaign Launch (Digital) | Digital Manager | 2024-04-16 | 2024-05-31 | Pending | $75,000 | Reach 1M impressions with CTR ≥ 3.5% | Not Started | 0%
Performance Review & Optimization Phase
4.1 | Monthly Performance Analysis | Data Analyst | 2024-05-01 | 2024-12-31 | Pending | $9,800 | Produce monthly reports with optimization recommendations | Not Started | 0%
Total Budget: | [5 empty] | $120,300