## Worksheet
Task ID | Task Name | Start Date | End Date | Assigned To | Status | % Complete
T001 | Market Research Analysis | 2024-04-01 | 2024-04-15 | John Doe | In Progress | 65%
T002 | Campaign Strategy Development | 2024-04-16 | 2024-04-30 | Jane Smith | Not Started | 0%
T003 | Create Marketing Materials | 2024-05-01 | 2024-05-15 | Mike Johnson | Not Started | 0%
T004 | Digital Campaign Launch | 2024-05-16 | 2024-06-15 | Sarah Brown | Not Started | 0%
T005 | Analyze Campaign Performance | 2024-06-16 | 2024-06-30 | John Doe | Not Started | 0%
Total | [5 empty] | 19%
Notes:This project plan is designed to outline key marketing activities. Tasks are tracked by status and percentage completion.
Last Updated:April 5, 2024