## Worksheet
Marketing Planning - Project Plan
Business Use Template ¦ Project Overview and Timeline
Phase / Task | Owner | Start Date | End Date | Status | Budget (USD) | Milestones/Notes
Market Research & Analysis | Marketing Team Lead | 2023-10-01 | 2023-10-15 | In Progress | $5,000 | Data collection and competitor benchmarking complete.
Target Audience Segmentation | Customer Insights Specialist | 2023-10-16 | 2023-10-25 | Pending | $3,500 | Focus groups scheduled for next week.
Marketing Strategy Development | Marketing Director | 2023-10-26 | 2023-11-05 | Pending | $7,000 | Draft approved by stakeholders.
Content Creation & Campaign Design | Copywriting & Creative Team | 2023-11-06 | 2023-11-25 | Pending | $15,000 | Visuals and copy under review.
Channel Planning & Media Buy | Media Coordinator | 2023-11-26 | 2023-12-05 | Pending | $45,000 | Budget approved for digital and print ads.
Launch & Campaign Execution | Project Manager | 2023-12-06 | 2024-01-31 | Pending | $65,000 | Main campaign rollout begins December 1st.
Total Project Budget: $140,500