## Worksheet
Marketing Planning - Project Plan (Client View)
Project ID: MKT-2024-001 ¦ Status: Active ¦ Prepared For: Client A
Phase | Task | Responsible Team | Start Date | End Date | Status | Budget (USD)
Initiation | Define Marketing Objectives | Marketing Strategy Team | 2024-04-01 | 2024-04-15 | In Progress | $5,000
Research & Analysis | Competitor Benchmarking | Market Research Unit | 2024-04-16 | 2024-05-15 | To Do | $8,500
Planning & Design | Create Campaign Concept & Creative Assets | Creative Design Team | 2024-05-16 | 2024-06-15 | To Do | $15,000
Development & Testing | Develop Digital Campaigns (Social, Email) | Digital Marketing Team | 2024-06-16 | 2024-07-15 | To Do | $20,000
Launch & Execution | Campaign Rollout - Phase 1 (Digital Channels) | Marketing Operations | 2024-07-16 | 2024-08-31 | To Do | $35,000
Evaluation & Optimization | Performance Analytics & KPI Review | Data Insights Team | 2024-09-01 | 2024-09-30 | To Do | $10,000
Total Project Budget: | [5 empty] | $93,500