## Worksheet
Task | Start Date | End Date | Owner | Status | Priority
Market Research & Analysis | 2023-10-01 | 2023-10-15 | Marketing Team | In Progress | High
Competitor Analysis | 2023-10-10 | 2023-10-25 | Market Analyst | Not Started | Medium
Target Audience Segmentation | 2023-10-15 | 2023-10-30 | Marketing Manager | Not Started | High
Campaign Strategy Development | 2023-10-25 | 2023-11-10 | Marketing Team | Not Started | High
Creative Asset Production | 2023-11-05 | 2023-11-20 | Design Team | Not Started | Medium
Channel Selection & Allocation | 2023-11-15 | 2023-11-25 | Media Planner | Not Started | High
Budget Planning & Approval | 2023-11-10 | 2023-11-30 | Finance & Marketing Lead | Not Started | High
Campaign Launch & Execution | 2023-12-01 | 2024-01-31 | Marketing Team | Not Started | High
Performance Monitoring & Reporting | 2024-01-01 | 2024-03-31 | Analytics Team | Not Started | Medium
Post-Campaign Review & Optimization | 2024-03-15 | 2024-04-15 | Marketing Director | Not Started | Medium