## Worksheet
Marketing Planning - Project Plan
Dashboard View ¦ Quarterly Campaign Management (Q3 2024)
Task ID | Task Description | Owner | Start Date | End Date | Status | Progress (%)
MKT-001 | Market Research & Competitor Analysis | Sarah Johnson | 2024-07-01 | 2024-07-15 | In Progress | 65%
MKT-002 | Create Campaign Strategy & Messaging | James Wilson | 2024-07-16 | 2024-07-31 | In Progress | 80%
MKT-003 | Design Visual Assets & Ad Creatives | Lisa Chen | 2024-08-01 | 2024-08-15 | Pending | 0%
MKT-004 | Develop Email & Social Media Campaigns | Tyler Reed | 2024-08-16 | 2024-09-15 | Pending | 0%
MKT-005 | Launch Digital Advertising (Google & Meta) | Alex Morgan | 2024-09-16 | 2024-10-31 | Pending | 0%
MKT-006 | Monitor KPIs & Optimize Campaign Performance | Nina Patel | 2024-11-01 | 2024-11-30 | Pending | 0%
MKT-007 | Final Reporting & Post-Campaign Review | Sarah Johnson | 2024-12-01 | 2024-12-15 | Pending | 0%
Overall Progress |  |  |  |  | Completed | 34%
Last updated on2024-07-15. Data reflects current project status across all marketing initiatives for Q3.