## Worksheet
Marketing Planning - Project Plan - Data Version
Phase | Task | Owner | Start Date | End Date | Status | Budget (USD) | Description
Phase 1: Planning
Planning | Define Marketing Objectives | Marketing Manager | 2024-04-01 | 2024-04-05 | In Progress | $5,000 | Establish clear KPIs and goals for the campaign.
Planning | Market Research & Analysis | Research Analyst | 2024-04-06 | 2024-04-15 | Pending | $8,500 | Gather data on customer demographics and trends.
Phase 2: Strategy Development
Strategy | Develop Target Audience Segmentation | Marketing Strategist | 2024-04-16 | 2024-04-25 | Pending | $6,000 | Create detailed personas for campaign targeting.
Strategy | Design Integrated Marketing Strategy | Marketing Manager | 2024-04-26 | 2024-05-10 | Pending | $7,500 | Craft a cohesive strategy across digital, social, and traditional media.
Phase 3: Execution
Execution | Content Creation (Digital) | Content Team | 2024-05-11 | 2024-05-31 | Pending | $15,000 | Create blog posts, videos, graphics, and ad copy.
Execution | Launch Social Media Campaign | Social Media Manager | 2024-06-01 | 2024-07-15 | Pending | $12,000 | Run targeted ad campaigns on Facebook, Instagram, and LinkedIn.
Phase 4: Monitoring & Evaluation
Monitoring | Track KPIs and Performance Metrics | Data Analyst | 2024-06-01 | 2024-07-31 | Pending | $4,500 | Monitor reach, engagement, conversions using analytics tools.
Evaluation | Final Performance Report & Recommendations | Marketing Director | 2024-08-01 | 2024-08-10 | Pending | $3,500 | Summarize results and provide insights for future planning.
Total Estimated Budget | [5 empty] | $62,000