## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (days) | Resource(s) | Status | % Complete | Description
1 | Define Marketing Objectives | 2023-10-01 | 2023-10-05 | 5 | Jane Smith (Marketing Director) | Completed | 100% | Establish clear, measurable goals for the marketing campaign.
2 | Market Research & Analysis | 2023-10-06 | 2023-10-15 | 10 | Mike Johnson (Research Analyst) | In Progress | 75% | Analyze industry trends, customer behavior, and competitor strategies.
3 | Create Target Audience Personas | 2023-10-16 | 2023-10-20 | 5 | Sarah Lee (Marketing Specialist) | In Progress | 50% | Develop detailed profiles of key customer segments.
4 | Develop Messaging & Brand Guidelines | 2023-10-21 | 2023-10-31 | 11 | Alex Chen (Brand Manager) | Not Started | 0% | Create consistent messaging frameworks and visual identity standards.
5 | Design Campaign Creative Assets | 2023-11-01 | 2023-11-15 | 15 | Lisa Wong (Graphic Designer), Tom Reed (Copywriter) | Not Started | 0% | Create visuals, videos, and copy for digital and print media.
6 | Select Marketing Channels & Platforms | 2023-11-01 | 2023-11-05 | 5 | Daniel Kim (Digital Strategist) | In Progress | 80% | Determine optimal channels based on audience reach and ROI.
7 | Prepare Budget & Allocate Resources | 2023-11-06 | 2023-11-10 | 5 | Fiona Brown (Finance Manager) | Not Started | 0% | Create detailed budget plan and secure approvals.
8 | Develop Launch Timeline & Milestones | 2023-11-11 | 2023-11-15 | 5 | Jane Smith (Marketing Director) | Not Started | 0% | Define key dates, deliverables, and review checkpoints.
9 | Campaign Pre-Launch Testing | 2023-11-16 | 2023-11-20 | 5 | All Team Members (QA) | Not Started | 0% | Test all materials, landing pages, and tracking systems.
10 | Campaign Launch (Phase 1) | 2023-11-21 | 2023-11-30 | 10 | Marketing Team (Full) | Not Started | 0% | Deploy initial marketing efforts across selected channels.
11 | Milestone Review & Optimization | 2023-12-01 | 2023-12-05 | 5 | Jane Smith, Alex Chen, Daniel Kim | Not Started | 0% | Analyze performance data and adjust strategy as needed.
12 | Campaign Expansion & Phase 2 Rollout | 2023-12-06 | 2024-01-15 | 41 | Full Marketing Team | Not Started | 0% | Broaden campaign reach and implement enhancements.
13 | Data Collection & Performance Reporting | 2024-01-16 | 2024-01-31 | 16 | Fiona Brown, Mike Johnson, Sarah Lee | Not Started | 0% | Gather and analyze campaign metrics for evaluation.
14 | Final Campaign Review & Lessons Learned | 2024-02-01 | 2024-02-15 | 15 | All Project Team Members | Not Started | 0% | Summarize outcomes, document successes and improvements.