## Worksheet
Marketing Planning - Extended Project Plan
Phase | Task / Activity | Owner | Start Date | End Date | Status | Budget (USD) | % Complete | Notes / Dependencies
Phase 1: Strategy & Research (Weeks 1–4)
Research | Market Analysis and Competitor Review | Marketing Analyst Team | 2025-04-07 | 2025-04-18 | In Progress | $3,500 | 75% | Requires access to CRM and industry reports.
Research | Customer Persona Development | User Experience Group | 2025-04-14 | 2025-04-25 | Not Started | $1,800 | 10% | Requires survey results from Q3.
Phase 2: Campaign Planning (Weeks 5–8)
Campaign Design | Create Messaging Framework & Brand Guidelines | Copywriting & Design Team | 2025-04-21 | 2025-04-30 | In Progress | $4,500 | 65% | Must align with brand audit results.
Campaign Planning | Develop 3 Campaign Concepts (Digital & Offline) | Marketing Strategy Team | 2025-04-28 | 2025-05-11 | Not Started | $6,000 | 5% | Milestone: Final concept approval by 2025-05-13.
Phase 3: Execution & Launch (Weeks 9–14)
Launch | Campaign Go-Live (Digital Channels) | Channel Managers | 2025-05-19 | 2025-05-19 | Scheduled | $48,000 | 3% | Limited to social media and email.
Phase 4: Performance & Review (Weeks 15–18)
Review | Analyze Campaign KPIs & ROI Report | Analytics Lead | 2025-06-02 | 2025-06-13 | Pending Review | $3,400 | 8% | Mandatory before budget approval for next cycle.
TOTAL BUDGET (All Phases) |  |  |  |  | $77,200