## Worksheet
Task ID | Task Name | Responsible Person | Start Date | End Date | Status | % Complete
MKT-001 | Market Research & Analysis | Jane Doe | 2025-04-01 | 2025-04-15 | In Progress | 75%
MKT-002 | Target Audience Identification | John Smith | 2025-04-16 | 2025-04-23 | To Do | 0%
MKT-003 | Create Brand Messaging Framework | Sarah Lee | 2025-04-18 | 2025-04-30 | In Progress | 60%
MKT-004 | Develop Marketing Campaign Strategy | Michael Brown | 2025-05-01 | 2025-05-14 | To Do | 0%
MKT-005 | Design Visual Assets & Content | Lisa Wong | 2025-05-15 | 2025-06-14 | To Do | 0%
MKT-006 | Launch Social Media Campaigns | David Kim | 2025-06-15 | 2025-07-31 | To Do | 0%
MKT-007 | Analyze Campaign Performance & Report | Jane Doe | 2025-08-01 | 2025-08-14 | To Do | 0%