## Worksheet
Marketing Planning
Project Plan ¦ Large Business Style
Phase / Task | Owner | Start Date | End Date | Status | Budget (USD)
Market Research & Analysis
Competitor Landscape Assessment | Marketing Analytics Team | 2024-04-01 | 2024-04-15 | In Progress | $8,500
Customer Persona Development | Consumer Insights Group | 2024-04-16 | 2024-04-30 | In Progress | $6,250
Campaign Strategy & Planning
Product Messaging Framework | Copywriting & Branding Team | 2024-05-01 | 2024-05-15 | In Progress | $9,750
Multi-Channel Campaign Plan (Digital & Print) | Media Planning Unit | 2024-05-16 | 2024-06-30 | Delayed | $45,980
Content Creation & Production
Video Ad Production (3x 30s) | Video Production Studio | 2024-06-01 | 2024-07-15 | Completed | $38,500
Website Landing Page Design & Optimization | Digital Creative Team | 2024-06-15 | 2024-07-31 | In Progress | $18,300
Launch & Execution Phase
Soft Launch (Beta Campaign) | Marketing Operations | 2024-08-01 | 2024-08-15 | Completed | $7,450
Full Market Launch & Media Blitz | Global Marketing Lead | 2024-08-16 | 2024-11-30 | Completed | $357,980
Performance Monitoring & Optimization
Monthly Performance Reports & KPI Review | Data Analytics Unit | 2024-09-01 | 2025-11-30 | In Progress | $36,578
Total Estimated Budget | $591,298