## Worksheet
Task | Start Date | End Date | Responsible | Status | Priority
Market Research & Analysis | 2023-10-01 | 2023-10-15 | Marketing Analyst Team | In Progress | High
Create Campaign Strategy | 2023-10-16 | 2023-10-31 | Marketing Manager | Pending Review | High
Develop Creative Assets | 2023-11-01 | 2023-11-20 | Design & Copywriting Team | In Progress | Moderate
Channel Selection & Budget Allocation | 2023-11-01 | 2023-11-10 | Budget Coordinator | Completed | High
Campaign Launch (Phase 1) | 2023-11-21 | 2023-12-05 | Marketing Team | Pending | High
Data Monitoring & Performance Tracking | 2023-11-21 | 2024-01-31 | Data Analyst Team | In Progress | Moderate
Mid-Campaign Review & Optimization | 2023-12-06 | 2023-12-15 | Marketing Manager | Pending | Moderate
Campaign Final Report & Insights Summary | 2024-01-01 | 2024-01-31 | Marketing Director | Pending | High