## Worksheet
Marketing Planning
Project Plan - Multi Page Template
Page 1: Project Overview
Project Name | Q4 2024 Global Marketing Campaign
Project Manager | Jane Doe
Status | In Planning Phase
Start Date | 2024-09-01
End Date | 2024-12-31
Total Duration | 4 months (16 weeks)
Budget | $500,000.00 USD
Page 2: Key Objectives
# | Objective | KPI Target | Measurement Method
1 | Increase brand awareness by 30% | +30% reach vs. Q3 2024 | Social media impressions & website traffic analytics
2 | Generate 15,000 qualified leads | 15,000 leads with form submission | Landing page conversion tracking & CRM data
3 | Grow email subscriber list by 25% | +25% new subscribers | Email marketing platform analytics (Mailchimp/HubSpot)
4 | Improve customer engagement rate by 20% | 20% increase in social media interactions | Engagement rate per post (likes, shares, comments)
5 | Drive $1.2M in new revenue from campaigns | $1.2M MRR from campaign-driven sales | Salesforce tracking & UTM parameters analysis
Page 3: Timeline & Milestones
Milestone | Due Date | Status | Owner
Project Kickoff Meeting | 2024-09-05 | Completed | Jane Doe (PM)
Market Research Finalized | 2024-09-15 | In Progress | Sarah Kim (Research Lead)
Brand Messaging Approved | 2024-09-30 | Pending | Michael Lee (Creative Director)
Campaign Assets Ready (Design & Copy) | 2024-10-15 | Pending | Taylor Chen (Design Team)
Launch Phase 1: Digital Ads & Social Media | 2024-10-20 | Pending | Jane Doe (PM)
Mid-Campaign Review (Week 8) | 2024-11-05 | Pending | Executive Team
Campaign Final Report & Optimization Plan | 2024-12-30 | Pending | Jane Doe (PM)
Page 4: Team Roles & Responsibilities
Role | Name | Department | Key Responsibilities
Project Manager | Jane Doe | Marketing Operations | Oversee entire project, manage timeline, budget, and cross-functional coordination.
Creative Director | Michael Lee | Creative Team | Lead branding & creative direction; approve all campaign visuals and copy.
Social Media Manager | Alice Johnson | Social Media | Manage social platforms, content calendar, engagement monitoring.
Digital Ads Specialist | Robert Taylor | Performance Marketing | Set up and optimize paid campaigns across Google Ads & Meta.
Email Marketing Lead | Lisa Wong | Email Campaigns | Design, deploy, and analyze email nurture sequences.
Research Analyst | Sarah Kim | Market Research | Capture insights from surveys, focus groups, and competitive analysis.
Page 5: Budget Allocation
Category | Budget (USD) | Percentage | Notes
Digital Advertising (Paid Media) | $250,000.00 | 50% | Google Ads, Meta, LinkedIn & programmatic display.
Content Creation (Design & Copy) | $75,000.00 | 15% | Graphics, videos, blog posts, landing pages.
Email Marketing Tools | $25,000.00 | 5% | Platform fees & automation tools.
Influencer Partnerships | $60,000.00 | 12% | Micro and macro influencers in target regions.
Events & Experiential Marketing | $55,000.00 | 11% | Virtual launch event & trade shows.
Miscellaneous / Contingency | $35,000.00 | 7% | Unplanned opportunities or adjustments.