## Worksheet
Marketing Planning - One Page Project Plan
Project Duration: January 2024 – December 2024 ¦ Prepared by: Marketing Team
Phase | Activity | Owner | Start Date | End Date | Status | Budget (USD)(Allocation) | Metric/Target
Research & Analysis | Market Research & Competitor Analysis | Marketing Analyst | Jan 1, 2024 | Feb 15, 2024 | In Progress | $8,500
Q1 Campaign Launch: Digital Ads & Social Media Blitz
Planning & Design | Create Campaign Creative & Copywriting | Graphic Designer, Content Writer | Feb 16, 2024 | Mar 10, 2024 | Not Started | $15,000
Execution | Launch Paid Ads (Google & Meta) | Digital Marketing Manager | Mar 11, 2024 | Apr 30, 2024 | Not Started | $50,000
Q2 Product Launch: Webinar Series & Influencer Outreach
Planning & Coordination | Schedule Webinars & Identify Influencers | Influencer Coordinator | May 1, 2024 | May 15, 2024 | Not Started | $7,500
Execution | Run 3 Webinars & Execute Influencer Campaigns | Digital Marketing Manager, Outreach Specialist | May 16, 2024 | Jun 30, 2024 | Not Started | $35,000
Q3 Expansion: Email Marketing & Retargeting Campaigns
Planning & Segmentation | Build Customer Segments & Email Funnel Design | Email Marketing Specialist | Jul 1, 2024 | Jul 15, 2024 | Not Started | $6,000
Execution | Run Retargeting & Automated Email Sequences | Email Marketing Specialist, Data Analyst | Jul 16, 2024 | Sep 30, 2024 | Not Started | $45,000
Q4 Consolidation: Performance Review & Strategy Refinement
Data Analysis | Collect & Analyze Campaign KPIs | Data Analyst, Marketing Manager | Oct 1, 2024 | Oct 31, 2024 | Not Started | $5,500
Reporting & Planning | Create Annual Report & Draft Next Year Plan | Marketing Director | Nov 1, 2024 | Dec 15, 2024 | Not Started | $8,000
Total Budget Allocated: | [5 empty] | $235,500