## Worksheet
Task ID | Task Description | Responsible Team Member(s) | Start Date | End Date | Status | Priority
T001 | Conduct Market Research & Analysis | Jane Smith, Alex Lee | 2024-04-01 | 2024-04-15 | In Progress | High
T002 | Define Target Audience Persona | Maria Garcia, Sam Patel | <2024-04-16 | 2024-04-25 | Pending | High
T003 | Create Brand Messaging Framework | Maria Garcia, Sam Patel, Alex Lee2024-04-182024-05-15 | In Progress | High
T004 | Design Marketing Campaign Assets | Lisa Wong, Jordan Kim | 2024-05-162024-06-15 | Pending | Medium
T005 | Publish Content Across Channels | Lisa Wong, Jordan Kim, Jane Smith2024-06-162024-07-31 | Pending | High
T006 | Analyze Campaign Performance Metrics | Alex Lee, Sam Patel, Lisa Wong2024-08-012024-08-15 | Pending | Medium
T007 | Prepare Final Marketing Report & Recommendations | Jane Smith, Maria Garcia, Alex Lee2024-08-162024-08-31 | Pending | High
Note:This is a personal use template for Marketing Planning. Adjust dates, team members, and tasks as needed.