## Worksheet
Marketing Planning - Project Plan
Phase | Task | Start Date | End Date | Status | Responsible Team/Person
Planning & Research Phase
1.1 | Market Research and Analysis | 2024-04-01 | 2024-04-15 | In Progress | Marketing Research Team
1.2 | Competitor Analysis Report Finalized | 2024-04-16 | 2024-04-30 | Pending | Strategy Department
Campaign Development Phase
2.1 | Create Campaign Concept & Messaging | 2024-05-01 | 2024-05-15 | Pending | Creative Team
2.2 | Develop Creative Assets (Videos, Graphics) | 2024-05-16 | 2024-06-15 | Pending | Creative Team
Execution Phase
3.1 | Launch Digital Advertising Campaign (Social Media, Google Ads) | 2024-06-16 | 2024-07-31 | Pending | Digital Marketing Team
3.2 | Execute Email Marketing Series (5 Emails) | 2024-06-18 | 2024-07-15 | Pending | Email Marketing Team
Monitoring & Reporting Phase
4.1 | Weekly Performance Tracking (KPIs, ROI, Engagement) | 2024-06-16 | 2024-07-31 | Pending | Data Analytics Team
4.2 | Final Campaign Performance Report & Recommendations | 2024-08-01 | 2024-08-15 | Pending | Marketing Manager
Notes:
This project plan is printable and designed for use as a structured marketing planning template.
Statuses: Pending, In Progress, Completed.
All dates are estimated and subject to change based on team availability and campaign performance.