## Worksheet
Marketing Planning - Project Plan
Phase | Task | Start Date | End Date | Status | Owner | Budget (USD)
Research & Analysis | Market Research and Competitor Analysis | 2023-10-01 | 2023-10-15 | In Progress | Jane Doe | $5,000
Strategy Development | Define Target Audience and Messaging | 2023-10-16 | 2023-10-31 | To Do | John Smith | $8,500
Content Creation | Develop Marketing Materials (Digital & Print) | 2023-11-01 | 2023-11-20 | To Do | Maria Lopez | $15,000
Channel Planning | Select and Optimize Marketing Channels (Social, Email, SEO) | 2023-11-21 | 2023-12-05 | To Do | Alex Brown | $7,500
Execution Phase 1 | Launch First Campaign (Social Media Blitz) | 2023-12-06 | 2024-01-15 | To Do | Sophia Reed | $18,000
Execution Phase 2 | Run Email Marketing and Retargeting Campaigns | 2024-01-16 | 2024-03-31 | To Do | Taylor Kim | $12,500
Monitoring & Optimization | Track KPIs and Adjust Campaigns Weekly | 2024-01-16 | 2024-04-30 | To Do | Daniel Clark | $6,800
Total Budget: | Sum of All Tasks: |  |  |  |  | $73,300