## Worksheet
Marketing Planning - Project Plan (Report Version)
Project ID: MKT-2024-001 ¦ Prepared on: May 5, 2024 ¦ Status: Draft
Task ID | Task Name | Start Date | End Date | Owner | Status | Budget (USD)
MKT-001 | Market Research & Analysis | 2024-05-10 | 2024-05-25 | Jane Smith (Research) | In Progress | $8,500
MKT-002 | Competitor Benchmarking | 2024-05-15 | 2024-06-15 | David Lee (Strategy) | Pending | $6,000
MKT-003 | Target Audience Definition | 2024-05-18 | 2024-06-15 | Sarah Chen (Marketing) | In Progress | $5,000
MKT-004 | Brand Messaging Development | 2024-06-16 | 2024-07-31 | Mike Johnson (Creative) | Pending | $15,000
MKT-005 | Content Creation (Digital & Print) | 2024-07-15 | 2024-10-31 | Lisa Wang (Content Team) | Pending | $35,000
MKT-006 | Marketing Campaign Launch | 2024-11-01 | 2024-11-30 | Team Lead (Marketing) | Pending | $75,000
MKT-007 | Performance Analysis & Reporting | 2024-12-01 | 2024-12-31 | Raj Patel (Analytics) | Pending | $18,500
Notes:
All dates are based on a fiscal year starting January 1, 2024.
Budget figures include labor, tools, and external services.
Status updated as of May 5, 2024. Actuals will be tracked monthly.