## Worksheet
Task | Start Date | End Date | Responsible | Status
Define Marketing Goals | 2023-10-01 | 2023-10-05 | Jane Doe | Completed
Conduct Market Research | 2023-10-06 | 2023-10-15 | John Smith | In Progress
Create Target Audience Profiles | 2023-10-16 | 2023-10-20 | Sarah Lee | Not Started
Develop Marketing Strategy | 2023-10-21 | 2023-10-31 | Jane Doe | Not Started
Design Marketing Materials | 2023-11-01 | 2023-11-10 | Alex Johnson | Not Started
Launch Campaign (Phase 1) | 2023-11-11 | 2023-11-25 | Maria Garcia | Not Started
Analyze Campaign Results | 2023-11-26 | 2023-12-05 | John Smith | Not Started
Adjust Strategy & Launch Phase 2 | 2023-12-06 | 2023-12-15 | Jane Doe | Not Started