## Worksheet
Marketing Planning - Startup Project Plan
Template Type: Project Plan ¦ Style/Version: Startup
Phase / Task | Start Date | End Date | Owner | Status | Budget (USD)
Market Research & Competitor Analysis | 2025-04-01 | 2025-04-15 | Jane Doe | In Progress | $3,500
Target Audience Segmentation | 2025-04-16 | 2025-04-25 | Mark Lee | Pending | $1,800
Brand Identity & Messaging Development | 2025-04-26 | 2025-05-10 | Sarah Kim | Pending | $4,700
Content Strategy & Calendar Planning | 2025-05-11 | 2025-06-15 | Liam Chen | Pending | $3,200
Social Media Campaign Launch (Phase 1) | 2025-06-16 | 2025-07-31 | Aisha Patel | Pending | $8,900
SEO & Digital Advertising Setup | 2025-07-01 | 2025-08-15 | James Wilson | Pending | $6,400
Email Marketing & Automation Integration | 2025-08-16 | 2025-09-15 | Sophie Grant | Pending | $3,800
Total Estimated Budget: |  |  |  |  | $32,300