## Worksheet
Project Phase | Key Activities | Responsible Team | Start Date | End Date | Status | Budget (USD)
Phase 1: Market Research & Analysis
Market Analysis | Conduct industry trend analysis, competitor benchmarking, customer segmentation | Marketing Research Team | 2024-01-05 | 2024-01-31 | In Progress | $8,500
Phase 2: Campaign Strategy Development
Target Audience Definition | Define buyer personas and customer journey mapping | Marketing Strategy Team | 2024-02-01 | 2024-02-15 | To Do | $6,300
Campaign Concept & Messaging | Develop core messaging themes and creative concepts for all channels | Creative Team | 2024-02-16 | 2024-03-15 | To Do | $15,750
Phase 3: Campaign Execution & Monitoring
Channel Planning & Allocation | Allocate budget and resources across digital, social, email, and traditional media | Media Planning Team | 2024-03-16 | 2024-03-31 | To Do | $55,000
Phase 4: Performance Evaluation & Reporting
Performance Metrics Setup | Define KPIs, tracking tools, and reporting dashboards | Data Analytics Team | 2024-04-01 | 2024-04-15 | To Do | $7,800
Total Project | Marketing Campaign Launch - Q2 2024 | [5 empty] | $93,350