## Worksheet
Marketing Planning - Project Plan - Tracking View
Task ID | Task Name | Owner | Start Date | Due Date | Status | Budget (USD) | Progress (%)
MKT-001 | Market Research & Analysis | Jane Smith | 2024-04-01 | 2024-04-15 | In Progress | $5,000 | 75%
MKT-002 | Competitor Benchmarking | Mike Johnson | 2024-04-05 | 2024-04-18 | In Progress | $3,500 | 65%
MKT-003 | Target Audience Segmentation | Sarah Lee | 2024-04-10 | 2024-04-25 | Pending | $2,800 | 15%
MKT-004 | Brand Messaging Development | David Brown | 2024-04-12 | 2024-05-03 | In Progress | $6,200 | 55%
MKT-005 | Social Media Campaign Launch | Lisa Wong | 2024-04-20 | 2024-05-15 | Pending | $15,000 | 5%
MKT-006 | Content Calendar Creation | Tom Harris | 2024-04-18 | 2024-05-10 | In Progress | $4,100 | 85%
MKT-007 | Website SEO Optimization | Anna Reed | 2024-04-25 | 2024-05-18 | Pending | $7,300 | 10%
MKT-008 | Email Marketing Strategy | Chris Evans | 2024-05-01 | 2024-05-31 | Pending | $8,600 | 3%
Total Budget: | [5 empty] | $62,500