## Worksheet
Marketing Planning - Project Template - Analysis View
Phase | Objective | Key Activities | Timeline (Weeks) | Responsible Team | KPIs/Success Metrics | Status
Planning & Research | Define target audience and market segments | Conduct customer surveys, analyze demographics, review competitive landscape | 1-2 | Market Research Team | Coverage of 90%+ target personas, 5+ competitor analysis reports | In Progress
| Set overall marketing goals and KPIs | Align with business objectives, define SMART goals (e.g., 20% increase in leads) | 3-4 | Marketing Strategy Team | Signed-off goal framework, measurable KPIs defined | Pending Review
| Develop initial budget allocation | Estimate costs for campaigns, channels, tools, and personnel | 5-6 | Finance & Marketing Ops | Budget approved by stakeholders; cost breakdown per channel visible | Completed
Campaign Design | Create campaign messaging and positioning framework | Develop value propositions, tone of voice guide, brand pillars | 7-8 | Brand & Creative Team | All core messages tested with focus groups; 90% approval rate | In Progress
| Design campaign assets (digital and print) | Produce banners, social posts, email templates, landing pages | 9-10 | Creative & Design Team | All assets delivered with final approvals; design system compliance confirmed | Pending Review
| Finalize channel mix and media plan | Decide on paid, owned, earned media allocation by platform (e.g., Google Ads, LinkedIn) | 11-12 | Media Planning Team | Budget distribution across channels; optimization strategy in place | Completed
Execution & Monitoring | Launch pilot campaign and monitor performance (first 2 weeks) | Deploy initial campaign, track engagement, CTR, conversion rates in real time | 13-14 | Campaign Management Team | Pilot CTR ≥ 2.5%, bounce rate ≤ 40% | In Progress
| Optimize based on early performance data | Adjust ad copy, targeting, bids; reallocate budget to top-performing channels | 15-16 | Data Analytics & Optimization Team | At least 3 optimizations made; improvement in CPA by ≥ 15% | Pending Review
Evaluation & Reporting | Compile full campaign performance report | Aggregate all data, calculate ROI, analyze attribution models | 17-18 | Data Science & Marketing Analytics Team | Fully documented report with visual dashboards; 95%+ accuracy in metrics | Completed
| Share insights and lessons learned with stakeholders | Present findings, recommend future improvements, archive assets for reuse | 19-20 | Marketing Leadership & Cross-functional Teams | All key stakeholders briefed; documented feedback collected | In Progress
Total Project Duration: 20 Weeks ¦ Status Summary: 5/7 Tasks Completed ¦ On Track