## Worksheet
Project Phase | Activity | Responsible Team/Person | Start Date | End Date | Status | Budget (USD)
Planning & Research | Market Analysis and Competitor Review | Marketing Research Team | 2024-04-01 | 2024-04-15 | In Progress | 5,000.00
Strategy Development | Create Marketing Objectives and KPIs | Marketing Strategy Team | 2024-04-16 | 2024-04-30 | To Do | 3,500.00
Content Creation | Develop Campaign Messaging and Creative Assets | Content & Design Team | 2024-05-01 | 2024-05-15 | To Do | 8,750.00
Channel Planning | Select and Schedule Distribution Channels | Digital Marketing Team | 2024-05-16 | 2024-05-31 | To Do | 6,300.00
Campaign Launch | Execute Marketing Campaign Across Channels | Marketing Operations Team | 2024-06-01 | 2024-06-30 | To Do | 55,000.00
Monitoring & Optimization | Analyze Performance and Adjust Strategies in Real Time | Data Analytics Team | 2024-06-15 | 2024-07-15 | To Do | 7,500.00
Evaluation & Reporting | Final Campaign Review and Performance Report Submission | Marketing Director & Analytics Team | 2024-07-16 | 2024-07-31 | To Do | 4,500.00
Total Estimated Budget: | [5 empty] | $90,550.00
Note:This template is designed for use in marketing planning projects with data tracking and reporting capabilities. Update statuses and dates as the project progresses.