## Worksheet
Marketing Planning - Project Template
Large Business Style ¦ Marketing Strategy & Execution Dashboard
Phase | Activity/Task | Owner | Start Date | End Date | Status | Budget Allocation (USD)(Monthly)
MARKETING STRATEGY & PLANNING
Phase 1 | Market Research & Analysis | Marketing Analytics Team | 2024-03-01 | 2024-03-15 | Active | $7,500(Q1)
Phase 1 | Competitor Benchmarking | Strategic Insights Unit | 2024-03-05 | 2024-03-18 | Active | $5,800(Q1)
CAMPAIGN DEVELOPMENT
Phase 2 | Brand Messaging Framework | Content & Creative Team | 2024-03-15 | 2024-03-31 | Active | $9,200(Q1)
Phase 2 | Campaign Concept Design & Approval | Marketing Director | 2024-03-18 | 2024-04-15 | Active | $11,500(Q2)
EXECUTION & DELIVERY
Phase 3 | Multi-Channel Launch (Digital + Print) | Digital Campaign Manager | 2024-04-15 | 2024-05-31 | On Hold | $87,600(Q2)
Phase 3 | Social Media Engagement Campaign | Social Media Specialist | 2024-04-15 | 2024-06-15 | Active | $38,900(Q2-Q3)
PERFORMANCE & OPTIMIZATION
Phase 4 | KPI Tracking & Reporting Dashboard | Data Analytics Lead | 2024-05-15 | 2024-12-31 | Active | $15,300(Q3-Q4)
Phase 4 | Monthly Optimization Review Meetings | Marketing Director & Team | 2024-06-01 | Ongoing (Monthly) | Active | $8,200(Q3-Q4)
FINAL REVIEW & REPORTING
Phase 5 | Post-Campaign Performance Analysis | Marketing Analyst | 2024-11-15 | 2024-12-31 | On Hold | $6,800(Q4)
TOTAL BUDGET SUMMARY
Total Estimated Budget: | [5 empty] | $239,800(Annual)