## Worksheet
Marketing Planning - Project Template (Manager View)
Project Phase | Key Activities | Owner | Scheduled Start | Scheduled End | Status | Progress (%)
Market Research & Analysis | Conduct customer surveys, competitor benchmarking, market trend analysis | Jane Doe - Market Analyst | 2024-01-15 | 2024-02-15 | In Progress | 65%
Objective Setting | Define SMART goals, KPIs, and target audience profiles | Mike Smith - Marketing Director | 2024-02-16 | 2024-03-01 | Completed | 100%
Channel Strategy Development | Determine optimal mix of digital, social, email, and traditional channels | Lisa Chen - Digital Strategist | 2024-03-02 | 2024-03-15 | In Progress | 75%
Budget Allocation & Forecasting | Allocate budget across channels, forecast ROI and expenses | Robert Brown - Finance Manager | 2024-03-16 | 2024-03-31 | Delayed | 45%
Tactical Campaign Planning | Create campaign calendars, content plans, and asset timelines | Emily Wilson - Campaign Manager | 2024-04-01 | 2024-05-15 | Completed | 100%
Implementation & Execution | Leverage tools and teams to launch campaigns across channels | Tony Reed - Project Lead | 2024-05-16 | 2024-08-31 | In Progress | 58%
Performance Monitoring & Optimization | Track KPIs, analyze results, and adjust campaigns in real-time | Sophia Lee - Analytics Lead | 2024-06-01 | 2024-12-31 | In Progress | 35%
Next Review Date:April 10, 2024
Last Updated:March 28, 2024