## Worksheet
Marketing Planning - Project Template (Report Version)
Project Phase | Activity | Timeline |  |  | Owner | Status
|  | Start Date | End Date | Durations (days)
Phase 1: Strategy Development | Market Research & Analysis | 2024-04-01 | 2024-04-15 | 15 | Jane Smith, Marketing Director | In Progress
| Campaign Objective & KPIs Definition | 2024-04-16 | 2024-04-25 | 10 | Michael Brown, Campaign Lead | Pending Approval
| Content & Design Creation (Assets) | 2024-04-26 | 2024-05-15 | 20 | Sarah Johnson, Creative Team Lead | Not Started
Phase 4: Media Planning & Allocation | Channel Selection & Budget Distribution | 2024-05-16 | 2024-05-31 | 16 | Alex Turner, Media Planner | Not Started
| Media Scheduling & Launch Coordination | 2024-06-01 | 2024-07-31 | 61 | Lisa Chen, Project Manager | Not Started
Phase 5: Performance Review & Optimization | Real-Time Campaign Monitoring & Reporting | 2024-06-01 | 2024-07-31 | 61 | Daniel Lee, Analytics Specialist | Not Started
| Post-Campaign Analysis & Final Report Preparation | 2024-08-01 | 2024-08-15 | 15 | Jane Smith, Marketing Director | Not Started
Total Project Duration |  | 150 days