## Worksheet
Marketing Planning - Startup Project Template
Template Type: Project Template ¦ Style/Version: Startup
Phase | Key Activities | Responsible Team | Timeline (Weeks) | Status
Market Research & Validation | Conduct target audience analysis | Marketing & Product Team | 1-2 | In Progress
| Create customer personas and buyer journeys | Marketing & UX Team | 2-3 | Pending
| Validate product-market fit via surveys and interviews | Data Analytics & Research Team | 3-4 | Pending
Go-to-Market Strategy | Define core messaging and value proposition | Marketing Team | 4-5 | Pending
| Develop channel-specific marketing plans (digital, social, email) | Digital Marketing Team | 5-6 | Pending
| Create initial campaign assets (landing pages, ads, content) | Content & Design Team | 6-7 | Pending
| Set up tracking and analytics infrastructure (UTM, Google Analytics) | Product & Tech Team | 7-8 | Pending
Launch Execution | Run pilot launch with early adopters (beta users) | Marketing & Customer Success Team | 8-9 | Pending
| Leverage influencer and community outreach campaigns | Influencer & Community Manager | 9-10 | Pending
| Optimize conversion funnels based on initial feedback | Data & Marketing Team | 10-12 | Pending
Growth & Scaling | Scale successful channels with increased budget allocation | Marketing & Finance Team | 12-16 | Pending
| Expand to new markets or customer segments | International & Product Teams | 15-20 | Pending
| Analyze KPIs and refine long-term strategy quarterly | Marketing & Strategy Team | Ongoing (Quarterly) | Pending
Note:This template is designed for startups and can be customized based on specific product, market, and team needs.