## Worksheet
Marketing Planning - Weekly Project Template
Week Start Date | Week End Date | Project Name | Status | Responsible Team Member(s)
Marketing Campaigns & Activities
Mon, Jan 1 | Fri, Jan 5 | Q1 Product Launch Campaign | In Progress | Alice Johnson, Mark Lee | Review campaign creatives and finalize landing page.
Mon, Jan 1 | Fri, Jan 5 | Social Media Content Calendar | Planned | Samira Patel, Chris Wong | Post weekly content across Instagram, LinkedIn & Twitter.
Mon, Jan 1 | Fri, Jan 5 | Email Marketing Series: Welcome Sequence | Completed | Laura Brown, Ryan Kim | Sent to 3K subscribers; open rate: 47%.
Mon, Jan 1 | Fri, Jan 5 | Google Ads Optimization | In Progress | Tony Garcia, Emma Davis | Adjust bids and targeting based on performance data.
Key Milestones & Deadlines
Jan 5 | Jan 5 | Campaign Launch Approval (Q1 Product) | Pending | Alice Johnson | Review with leadership team.
Jan 8 | Jan 8 | Social Media Analytics Report (Week 1) | Pending | Samira Patel | Analyze engagement trends and adjust strategy.
Notes & Action Items
• Confirm budget allocation for paid channels by Jan 4. • Schedule weekly sync meeting every Monday at 10:00 AM. • Update tracking links in all digital assets before campaign go-live.
Prepared By
Marketing Manager: Sarah Thompson Date: Jan 1, 2024 Version: Weekly Template v1.0