## Worksheet
Marketing Planning - Project Timeline
Phase / Task | Start Date | End Date | Status | Owner(s) | Priority | Budget (USD)
Market Research & Analysis | 2024-01-05 | 2024-01-25 | In Progress | Jane Doe, Mark Lee | High | $8,500
Competitor Benchmarking Report | 2024-01-05 | 2024-01-15 | Completed | Jane Doe | Medium | $3,000
Target Audience Segmentation | 2024-01-16 | 2024-01-25 | In Progress | Mark Lee, Sarah Kim | High | $5,500
Brand Positioning & Messaging | 2024-01-26 | 2024-02-15 | Delayed | Sarah Kim, David Chen | High | $15,000
Value Proposition Development | 2024-01-26 | 2024-02-15 | Delayed | Sarah Kim | High | $8,000
Core Messaging Framework Draft | 2024-01-31 | 2024-02-15 | Delayed | Daniel Park, Lisa Tran | High | $7,000
Marketing Campaign Design | 2024-02-16 | 2024-03-31 | In Progress | Alex Morgan, Olivia Rivera | High | $45,000
Content Strategy & Calendar Creation | 2024-02-16 | 2024-03-15 | In Progress | Alex Morgan, Emily Wu | Medium | $8,000
Visual Asset Production (Graphics & Videos) | 2024-03-15 | 2024-03-31 | In Progress | Olivia Rivera, Michael Brown | High | $37,000
Campaign Launch & Execution | 2024-04-01 | 2024-06-30 | Completed | Ryan Patel, Sophia Liu | High | $150,000
Multi-Channel Launch (Social, Email, SEO) | 2024-04-01 | 2024-05-31 | Completed | Ryan Patel, Sophia Liu | High | $95,000
Performance Monitoring & Optimization | 2024-04-15 | 2024-06-30 | Completed | Ryan Patel, David Chen | Medium | $55,000
Post-Campaign Review & Reporting | 2024-07-01 | 2024-07-15 | Completed | Jane Doe, Mark Lee | Low | $6,000
Total Budget: | $348,500