## Worksheet
Phase | Task | Start Date | End Date | Status | Owner | Metric / KPI
Research & Analysis | Market Research Initiation | 2023-09-01 | 2023-09-15 | In Progress | Jane Doe | Survey Response Rate ≥ 75%
| Competitor Analysis Completion | 2023-09-16 | 2023-10-05 | On Track | John Smith | Coverage of 8+ Competitors
| Customer Persona Development | 2023-10-06 | 2023-10-15 | On Track | Sarah Lee | Finalized 4 Core Personas
| Research Review & Approval | 2023-10-16 | 2023-10-20 | Not Started | Jane Doe | All Deliverables Reviewed and Signed Off
Strategy Development | Marketing Goals & Objectives Setting | 2023-10-21 | 2023-11-05 | Not Started | Jane Doe | S.M.A.R.T. Goals Defined for Q4 2023
| Channel Strategy Planning | 2023-11-06 | 2023-11-15 | Not Started | John Smith | All 5 Channels Allocated Budget & KPIs Assigned
| Strategy Presentation & Approval | 2023-11-16 | 2023-11-20 | Not Started | Sarah Lee | Presentation Reviewed by Leadership Team
Campaign Execution | Campaign Creative Development (Phase 1) | 2023-11-21 | 2023-12-05 | Not Started | Sarah Lee | 5+ Assets Finalized for Launch
| Campaign Launch: Social Media & Email (Q4) | 2023-12-06 | 2023-12-15 | Not Started | John Smith | Audience Reach ≥ 50,000 Impressions/Week
| Campaign Launch: Paid Ads (Google & LinkedIn) | 2023-12-16 | 2023-12-31 | Not Started | Jane Doe | CPC ≤ $0.85, CTR ≥ 4%
| Content Calendar Activation (Monthly) | 2023-12-06 | 2024-01-31 | Not Started | Sarah Lee | All Monthly Posts Scheduled & Approved
| Mid-Campaign Performance Review (Week 6) | 2024-01-01 | 2024-01-15 | Not Started | Jane Doe | Performance Data Analyzed & Adjustments Recommended
Evaluation & Reporting | Final Campaign Performance Analysis (Q4) | 2024-01-16 | 2024-01-31 | Not Started | Sarah Lee | Campaign ROI ≥ 5:1, CPA ≤ $85
| Post-Campaign Report & Presentation to Stakeholders | 2024-02-01 | 2024-02-15 | Not Started | Jane Doe | All Key Insights & Recommendations Delivered
Overall Project Status: On Track (Q4 2023) | [5 empty] | Next Review: February 1, 2024