## Worksheet
Marketing Planning - Project Timeline
Phase | Task Description | Start Date | End Date | Status | Responsible Team/Person
Planning & Research | Conduct market research and competitor analysis | 2024-04-01 | 2024-04-15 | In Progress | Marketing Research Team
Strategy Development | Define marketing goals and target audience | 2024-04-16 | 2024-04-30 | To Do | Marketing Manager
Campaign Design | Create promotional content and campaign materials | 2024-05-01 | 2024-05-15 | To Do | Creative Team
Budget Allocation | Finalize budget and resource allocation | 2024-05-16 | 2024-05-20 | To Do | Finance & Marketing Coordinators
Implementation | Lunch digital and traditional marketing campaigns | 2024-05-21 | 2024-06-30 | To Do | Marketing Execution Team
Monitoring & Evaluation | Analyze campaign performance and adjust strategies | 2024-07-01 | 2024-07-15 | To Do | Data Analysts & Marketing Team
Reporting & Review | Prepare final report and conduct post-mortem meeting | 2024-07-16 | 2024-07-31 | To Do | Marketing Director & Project Lead