## Worksheet
Marketing Planning - Project Timeline (Client View)
Phase | Task | Start Date | End Date | Status | Budget (USD)
Market Research & Strategy Development
Research Phase | Competitor Analysis | 2023-10-01 | 2023-10-15 | Completed | $8,500
Research Phase | Customer Persona Development | 2023-10-16 | 2023-10-31 | Completed | $7,200
Research Phase | Marketing Strategy Finalization | 2023-11-01 | 2023-11-15 | In Progress | $6,800
Campaign Execution & Launch
Campaign Phase 1 | Content Creation (Social Media) | 2023-11-16 | 2023-12-05 | In Progress | $9,500
Campaign Phase 1 | Ad Campaign Launch (Google Ads) | 2023-11-20 | 2023-12-15 | In Progress | $14,700
Campaign Phase 1 | Email Marketing Series - Part 1 | 2023-12-06 | 2023-12-15 | Delayed | $4,300
Performance Review & Optimization
Review Phase | Performance Analytics Report (Week 1) | 2023-12-16 | 2024-01-05 | In Progress | $5,900
Review Phase | Optimization & A/B Testing Adjustments | 2024-01-06 | 2024-01-31 | Delayed | $7,600
Review Phase | Final Report & Client Presentation | 2024-02-01 | 2024-02-15 | Pending | $8,900
Total Estimated Budget: |  |  |  |  | $83,200
Note:This timeline is for client viewing and reflects current status as of October 1st, 2023. Status indicators are subject to change based on project progress.